## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished
1 | Prototype Glasses Screen | 4 | 5
2 | Research Glasses API | 8 | 1 | 1
3 | Understand Previous Group's Model | 5 | 4 | 1
4 | Research Sending data to Glasses |  | 3 | 1
5 | Research ELO tablet, try to emulate it in Android Studio | 3 | 2 | 1
6 | Prelim App UI Design | 3 | 1 | 1
7 | Research python in Android Studio |  | 2 | 1
8 | Use Synergy Practice API |  | 3 | 1
9 | Create Android Studio App, Link to Github | 3 | 1 | 1
10 | Design Info Delivery System | 12 | 1 | 1
11 | UI App Updates | 12 | 1 | 2
12 | Create Sample get request | 6 | 2 | 2
13 | Connect to SmartGlasses | 6 | 4 | 2
14 | Write Python code for Android Studio | 8 | 3 | 2
15 | Deploy app onto tablet | 4 | 1 | 2
16 | Use Screen mirroring software to show tablet on PC | 2 | 1 | 2
17 | Set up Synergy Account and Find Resources For Request Syntax | 6 | 1 | 2
18 | Finalize Synergy Data formatting | 4 | 1 | 3
19 | Write to shared file or exposed endpoint | 3 | 2 | 3
20 | Read Python output in Kotlin | 5 | 1 | 3
21 | Map stats to display-friendly text | 4 | 1 | 3
22 | Scan and discover Frame glasses via BLE | 6 | 1 | 3
23 | Identify Frame service/char UUIDs | 4 | 2 | 3
24 | Add extra stat calculations | 4 | 3 | 3
25 | Android UI polish | 3 | 3 | 3
26 | Link button actions to display logic | 5 | 1 | 3
27 | Add status feedback (BLE connected, sent) | 2 | 3
28 | Sprint 3 documentation | 4 | 1 | 3
29 | Update team website | 3 | 2